## Lead
Project Name:
Housekeeper Scheduling System
Group Number: 5 (DP)
Total Members: 10
Team Lead: Shraddha Rajguru
Front-End Lead: Sumit Kumar
Back-End Lead: Harshal jumnake

## Status Track
Sl No. | Employee ID | Name | Domain | Module | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-09 | 2022-05-10 | 2022-05-11
1 | 2496376 | Harshal Waman Jumnake | Database | Admin | Task Distribution | Started working on Admin Module | Admin Registration table | Allot Table | Completed Admin Databases and configure | Prepared PPT and Completed Remaining tasks of Everyone and also conducted a mock presentation in Evening.
2 | 2494660 | Sumit Kumar | Front-End | Admin | Task Distribution | Started working on Admin Module | Child Class | Admin login and logout | Completed Admin all modules and Configure
3 | 2498325 | Anuka | Testing | Test Cases | Task Distribution | Started working on Package Module | Admin and repo in entity | Main Method | Wrote all test cases
4 | 2496337 | Yalabolu Haripriya | Front-End | Package | Task Distribution | Started working on Package Module | User Dashboard | Register Students | User Feedback
5 | 2498767 | Shraddha Pankaj Rajguru | Front-End | User | Task Distribution | Started working on User Module | Admin Dashboard | Register Housekeeper | Completed User all modules and configure
6 | 2498833 | Voira S.Venkata Pavan Kumar | Testing | Test Cases | Task Distribution | Started working on Package Module | User and repo in entity | Control Testing | Wrote all test cases
7 | 2498867 | Mohmad Fahim Shaikh | Database | User | Task Distribution | Started working on User Module | User Table | User Feedback table | Completed user Databases and configure
8 | 2496081 | Teki Jaswant | Back-End | Admin | Task Distribution | Started working on Admin Module | Admin and repo in entity | Services for Admin | Completed Admin Modules & configure BE to FE
9 | 2497806 | Uppalapati Kumari | Back-End | User | Task Distribution | Started working on User Module | User and repo in entity | Services for User | Completed all controller API test
10 | 2496206 | Mohd Asra | Back-End | Package | Task Distribution | Started working on Admin Module | Admin and repo in entity | Services for user | Completed User Modules & Congigure BE to FE

## Status Meeting
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2022-05-05 | 10 A.M. | ü | 2 P.M. | ü | 5 P.M. | ü
2022-05-06 | 9:30 A.M. | ü | 12 P.M. | ü | 5 P.M. | ü
2022-05-07 | 9:30 A.M. | ü | 12 P.M. | ü | 5 P.M. | ü
2022-05-09 | 10 A.M. | ü | 12:30 P.M. | ü | 6 P.M. | ü
2022-05-10 | 9:30 A.M. | ü | 12:30P.M. | ü | 6 P.M. | ü
2022-05-11 | 9:30 A.M. | ü | 2 P.M. | ü | 5 P.M. | ü